## Sheet 1
Week | Dates | Milestone / Task | Status | Notes
1 | Jul 22–Jul 28 | Finalize spec sheet: Gain range, input/output swing, power budget | TRUE | Consult examples on Peter KInget site
2 | Jul 29–Aug 04 | Design two-stage Miller OTA with compensation | FALSE | Ensure phase margin > 60°
3 | Aug 05–Aug 11 | Add programmable gain block | FALSE | Consult paper by Joe Buxton
4 | Aug 12–Aug 18 | Simulate full signal chain: transient, AC, noise, corners | FALSE | Focus on SFDR, gain error
5 | Aug 19–Aug 25 | Begin layout of amplifier core | FALSE | Stick to GF180 PDK rules
6 | Aug 26–Sep 01 | Route programmable gain logic + switches | FALSE | Check parasitic effects
7 | Sep 02–Sep 08 | Run LVS/DRC, fix bugs | FALSE | Use PEX to verify post-layout perf
8 | Sep 09–Sep 15 | Integrate with Mosbius top level | FALSE | Match input/output specs
9 | Sep 16–Sep 22 | Final testing, cleanup, documentation, submission | FALSE | Submit on or before deadline

## Sheet 2
Hierarchy Level | Cell / Block | Schematic + Sims | Layout | Post-Layout Sims
1 | Two Stage OTA | 50% | 0% | 0%
1 | Class AB output | 50% | 0% | 0%
1 | Complete two stage Op-Amp | 0% | 0% | 0%
2 | Gain Block | 0% | 0% | 0%
2 | Top Level Integration | 0% | 0% | 0%
2 | Layout (LVS/DRC checks) | 0% | 0% | 0%
3 | Final Documentation | 0% | 0% | 0%